|  |  |
| --- | --- |
| **Request for Tender:** | Big Shed Additions & Alterations |
|  |  |
| **Deadline:** | Monday 17th March 2025 at 2.00pm  Western Australian Standard Time |
|  |  |
| **Address for Delivery:** | PO Box 20  52 Hesse Street  Waroona WA 6215  warshire@waroona.wa.gov.au  *Email tenders will be accepted* |
|  |  |
| **RFT Number:** | 202425-04 |

1. Conditions of Tendering 5

1.1. Contract Requirements in Brief 5

1.2. Definitions and Interpretations 5

1.3. Tender Documents 6

1.4. How to Prepare Your Tender 6

1.5. Contact Persons 6

1.6. Value for Money 7

1.7. Deposits for Requests 7

1.8. Site Inspection 7

1.9. Customs Duty 7

1.10. Site Allowances 7

1.11. Lodgement of Tenders and Delivery Method 8

1.12. Rejection of Tenders 8

1.13. Acceptance of Tenders 8

1.14. Disclosure of Contract Information 8

1.15. Tender Validity Period 8

1.16. Precedence of documents 8

1.17. Alternative Tenders 9

1.18. Tenderers to Inform Themselves 9

1.19. Alterations 9

1.20. Risk Assessment 9

1.21. Evaluation Process 10

1.22. Selection Criteria 10

1.23. Compliance Criteria 11

1.24. Qualitative Criteria 11

1.25. Value Considerations 11

1.26. Regional Price Preference 11

1.27. Price Basis 12

1.28. Ownership of Tenders 13

1.29. Canvassing of Officials 13

1.30. Identity of the Tenderer 13

1.31. Costs of Tendering 13

1.32. Tender Opening 13

1.33. In-house Tenders 13

2. Statement of Requirements 14

2.1. Introduction 14

2.2. Background 14

2.3. Definitions and Interpretations 14

2.4. Scope of Work 14

2.5. Drawings and Specifications 15

2.6 Implementation Timetable 16

2.7 Contract Documents 16

2.8 Reporting and Records 17

2.9 Goods and Services Tax (GST) 17

3. Conditions of Contract 18

3.1 Terms and Conditions of Contract 18

3.2 Contract Schedules 18

3.3. SEPARABLE PORTIONS – Not Applicable 21

3.4. Insurances 21

3.5. Period of Contract Termination 21

4. Special Conditions of Contract 22

4.1. Advertisements and Promotions on Site 22

4.2. Site Access 22

4.3. Publicity 22

4.4. Documents Generally, Drawings and Specifications 22

4.4.1. Copies of Documents 22

4.4.2. Drawings 22

4.5. Environmental Protection 22

4.5.1. Noise Control 22

4.5.2. Site Control 23

4.5.3. Soil Erosion 23

4.5.4. Dust, Dirt, Water and Fumes 23

4.5.5. Vehicles 23

4.5.6. Refuse Disposal 23

4.5.7. Smoking on Construction Sites 23

4.6. Contractor’s Representative 24

4.7. Existing Improvements 24

4.8. Temporary Safety Fence 24

4.9. Materials, Labour and Constructional Plan 24

4.9.1. Workmen’s Amenities 24

4.10. Materials and Work 24

4.10.1. Regulations 24

4.10.2. Chemical Information 25

4.10.3. Trade Names 25

4.10.4. Safety Management Plan 25

4.10.5. Induction Training 25

4.10.6. Pre-Job Planning 25

4.10.7. Materials to be Supplied by the Principal 26

4.10.8. Working Hours 26

4.10.9. Schedule of Warranties 26

4.10.10. Goods and Services Tax (GST) 26

4.10.11. BCITF Levy 26

5. Tenderer’s Offer 28

5.1. Form of Tender 28

5.2. Price Schedule 29

5.3. General and Corporate Information 30

5.4. Organisational Profile and Referees 30

5.5. Agents 30

5.6. Trusts 31

5.7. Sub-Contractors 31

5.8. Conflicts of Interest 31

5.9. Work Health and Safety 31

5.10. Financial Position 31

5.11. Quality Assurance System 32

5.12. Insurance Coverage 32

5.13. Selection Criteria 33

5.13.1. Compliance Criteria 33

5.13.2. Qualitative Criteria 33

5.14. Price Information 34

5.15. Discounts 35

5.16. Price Basis 35

5.17. Regional Preference 35

6. Contractor’s Work Health and Safety Management System Questionnaire 36

7. Tenderer’s Resource Schedule 39

7.1. Tenderer’s Current Commitment Schedule 39

8. Appendix A – Architectural works specification 40

9. Appendix B – Electrical works specification 41

10. Appendix C – Hydraulics works specification 42

11. Appendix D – Structural works specification 43

12. Appendix E – Drawings 44

# Conditions of Tendering

## 1.1. Contract Requirements in Brief

The Principal is seeking submissions to the Shire of Waroona for construction works for the additions and alterations to the existing BIG Shed and construction of a freestanding shelter located at Lot 1 Fouracre Street, Waroona, 6215

Full details of the scope of works required under the proposed Contract appears in the Statement of Requirements section.

Submitters are to ensure that ALL relevant forms in the Tender document have been completed and duly signed.

## Definitions and Interpretations

Below is a summary of some of the important defined terms used in this Request:

|  |  |
| --- | --- |
| **Attachments:** | The documents you attach as part of your Tender. |
| **Contractor:** | Means the person or persons, corporation or corporations who’s Response is accepted by the Principal, and includes the executors or administrators, successors and assignments of such person or persons, corporation or corporations. |
| **Deadline:** | The Deadline shown on the front cover of this Request for lodgement of your Tender. |
| **General Conditions of Contract:** | Means the General Conditions of Contract for the Waroona BIG SHED additions and alterations in Part 3. |
| **Offer:** | Your Offer to supply the Requirements. |
| **Principal:** | Shire of Waroona |
| **Request or RFQ or Request for Quotation:** | This document. |
| **Requirement:** | The Waroona BIG SHED additions and alterations requested by the Principal. |
| **Selection Criteria:** | The Criteria used by the Principal in evaluating your Tender. |
| **Special Conditions:** | The additional contractual terms. |
| **Specification:** | The Statement of Requirements that the Principal requests you to provide if selected. |
| **Tender:** | Completed Offer form, Response to the Selection Criteria and Attachments. |
| **Tenderer:** | Someone who has or intends to submit an Offer to the Principal. |
| **Tender Open Period:** | The time between advertising the Request and the Deadline. |

## 1.3. Tender Documents

This Request for Tender is comprised of the following parts:

* Part 1 - Conditions of Tendering *(read and keep this part)*.
* Part 2 - Statement of Requirements *(read and keep this part)*.
* Part 3 - General Conditions of Contract *(read and keep this part)*.
* Part 4 - Special Conditions of Contract *(read and keep this part)*.
* Part 5 - Tenderer’s Offer *(complete and return this part)*.
* Part 6 - Contractor’s Work Health and Safety Management System Questionnaire (complete and return this part).
* Part 7 - Tenderer’s Safety Record *(complete and return this part).*
* Part 8 - Project Reference Sheet *(complete and return this part).*
* Part 9 - Tenderer’s Resources Schedule *(complete and return this part).*
* Part 10 – Appendices *(read and keep this part).*
* Appendix A Architectural works specification
* Appendix B Electrical works specification
* Appendix C Hydraulics works specification
* Appendix D Structural works specification
* Appendix E Drawings

**Separate Documents**

1. Addenda and any other special correspondence issued to Tenderers by the Principal.
2. Any other policy or document referred to but not attached to the Request.

## 1.4. How to Prepare Your Tender

1. Carefully read all parts of this document;
2. Ensure you understand the Requirements;
3. Complete and return the Offer (Part 3) in all respects and include all Attachments;
4. Make sure you have signed the Offer form and responded to all of the Selection Criteria; and
5. Lodge your Tender before the Deadline.

## Contact Persons

Tenderers should not rely on any information provided by any person other than the person(s) listed below:

|  |  |
| --- | --- |
| **Name:** | Wayne Prangnell, Project Manager |
| **Telephone:** | 0419 917 165 |
| **Email:** | [warshire@waroona.wa.gov.au](mailto:warshire@waroona.wa.gov.au) |

## Value for Money

In accordance with the Shire of Waroona’s Purchasing and Procurement Policy FP001 the procurement process shall ensure that a best value for money outcome is attained. The Shires policy can be found at:

<https://www.waroona.wa.gov.au/documents/11955/fp001-purchasing-and-procurement>

Value for money is determined when the consideration of price, risk and qualitative factors that are assessed, results in the most advantageous outcome being achieved. The qualitative criteria used for assessment purposes is provided in Part 5 Tenderers Offer.

The assessment of the best value for money outcome shall, as applicable, consider:

* All relevant total costs
* The technical merits
* Financial viability and capacity to supply without risk of default
* Competition
* Safety requirements
* Sustainable benefits
* Providing opportunities for businesses within the Shire’s boundaries

## Deposits for Requests

Not applicable.

## Site Inspection

Tenderers are invited to attend a Site Inspection and to inspect recycled jarrah timber at the Shire’s Hesse Street Depot. The site inspection will be held on 27th February meeting at the Shire’s Hesse St Depot at 9:30am for inspection of recycled timber and then 10:00am at the site of the works on Fouracre St. Please RSVP for the site inspection and address enquiries to the Project Manager Wayne Prangnell at [warshire@waroona.wa.gov.au](mailto:warshire@waroona.wa.gov.au) or phone 0419 917 165.

The tenderer, by submission of his tender, acknowledges that he has and shall be deemed to have, inspected the site and determined and allowed for all conditions on and surrounding the site including, but not limited to, access, location and condition of all above ground services, and materials requiring demolition and removal all as found at the time of tender and as may affect the carrying out of the contract.

## Customs Duty

The Tenderer shall allow for any customs duty and primage applicable to all imported materials, plant and equipment required in connection with the works in its Tender.

## Site Allowances

This contract is not subject to adjustment for Site allowances.

## Lodgement of Tenders and Delivery Method

The tender must be lodged before the Deadline. The Deadline for this request is 2pm Monday 17th March 2025.

The Tender shall be sent as an email to [warshire@waroona.wa.gov.au](mailto:warshire@waroona.wa.gov.au)

Tenders will be accepted provided that no individual email with attachments is more than 10Mb in total. For email Tenders greater than 10Mb they must be sent in separate emails less than 10Mb each.

## Rejection of Tenders

A Tender may be rejected at the sole discretion of the Principal without consideration of its merits in the event that:

1. it is not submitted before the Deadline; or
2. it is not submitted at the place specified in the Request; or
3. it may be rejected if it fails to comply with any other requirements of the Request.

No web links or hyperlinks will be considered as part of any submission.

## Acceptance of Tenders

Unless otherwise stated in this Request, Tenders may be for all or part of the Requirements and may be accepted by the Principal either wholly or in part. The Principal is not bound to accept the lowest Tender and may reject any or all Tenders submitted.

## Disclosure of Contract Information

Documents and other information relevant to the contract may be disclosed when required by law under the *Freedom of Information Act 1992* or under a Court order.

All Tenderers will be given particulars of the successful Tenderer and be advised that no Tender was accepted.

## Tender Validity Period

All Tenders will remain valid and open for acceptance for a minimum period of one hundred and twenty (120) calendar days from the Deadline or forty-five (45) calendar days from the Principal’s resolution for determining the Tender, whichever is the later unless extended on mutual agreement between the Principal and the Tenderer in writing.

## Precedence of documents

In the event of there being any conflict or inconsistency between the Terms and Conditions herein and those in the General Conditions of Contract, the Terms and Conditions appearing in this Request will have precedence.

## Alternative Tenders

All Alternative Tenders must be accompanied by a conforming Tender.

Tenders submitted as Alternative Tenders or made subject to conditions other than the General and Special Conditions of Contract must in all cases be clearly marked “**Alternative Tender**”.

The Principal may in its absolute discretion reject any Alternative Tender.

Any printed “General Conditions of Contract” contained within a Tender will not be binding on the Principal in the event of a Contract being awarded unless the Tender is marked as an Alternative Tender.

## Tenderers to Inform Themselves

Tenderers will be deemed to have:

1. examined the Request and any other information available in writing to Tenderers for the purpose of tendering;
2. examined all further information relevant to the risks, contingencies, and other circumstances having an effect on their Tender which is obtainable by the making of reasonable enquires;
3. satisfied themselves as to the correctness and sufficiency of their Tenders including tendered prices which will be deemed to cover the cost of complying with all the Conditions of Tendering and of all matters and things necessary for the due and proper performance and completion of the work described therein;
4. acknowledged that the Principal may enter into negotiations with a chosen Tenderer and that negotiations are to be carried out in good faith;
5. satisfied themselves they have a full set of the Request documents and all relevant attachments; and
6. undertaken a site inspection to familiarise themselves with the project requirements and the site.
7. Inspected the recycled jarrah timber at the Shire’s Hesse Street Depot

## Alterations

The Tenderer must not alter or add to the Request documents unless required by these General Conditions of Tendering.

The Principal will issue an addendum to all registered Tenderers where matters of significance make it necessary to amend the issued Request documents before the Deadline.

## Risk Assessment

The Principal may have access to and give consideration to:

1. any risk assessment undertaken by any credit rating agency;
2. any financial analytical assessment undertaken by any agency; and
3. any information produced by the Bank, financial institution, or accountant of a Tenderer;

so as to assess that Tender and may consider such materials as tools in the Tender assessment process.

Tenderers may be required to undertake or provide to the Principal (or its nominated agent) upon request all such information as the Principal reasonably requires to satisfy itself that Tenderers are financially viable and have the financial capability to provide the Services for which they are submitting and meet their obligations under any proposed Contract. The Principal reserves the right to engage (at its own cost) an independent financial assessor as a nominated agent to conduct financial assessments under conditions of strict confidentiality. For this assessment to be completed, a representative from the nominated agent may contact Tenderers concerning the financial information that they are required to provide.

The financial assessment is specifically for use by the Principal for the purpose of assessing Tenderers and will be treated as strictly confidential.

## Evaluation Process

Tenders will be evaluated using information provided in the Tender.

The following evaluation methodology will be used in respect of this Request:

1. Tenders are checked for completeness and compliance. Tenders that do not contain all information requested (e.g. completed Offer form and Attachments) may be excluded from evaluation.
2. Tenders are assessed against the Selection Criteria. Contract costs are evaluated (e.g. tendered prices) and other relevant whole of life costs are considered.
3. The most suitable Tenderers may be short listed and may also be required to clarify their Tender, make a presentation, demonstrate the product/solution offered and/or open premises for inspection. Referees may also be contacted prior to the selection of the successful Tenderer.

A Contract may then be awarded to the Tenderer whose Tender is considered the most advantageous Tender to the Principal.

## Selection Criteria

The Contract may be awarded to a sole Tenderer who best demonstrates the ability to provide quality products and or services at a competitive price. The tendered prices will be assessed together with the qualitative and compliance criteria to determine the most advantageous outcome to the Principal.

The Principal has adopted the best value for money approach to this Request. This means that, although price is considered, the Tender containing the lowest price will not necessarily be accepted, nor will the Tender ranked the highest on the Qualitative Criteria.

A scoring system will be usual as part of the assessment of the Qualitative Criteria. Unless otherwise stated, a Tender which provides all the information requested will be assessed as satisfactory.

The extent to which a Tender demonstrates greater satisfaction of each of these criteria will result in a greater score. The aggregate score of each Tender will be used as one of the factors in the final assessment of the Qualitative Criteria and in the overall assessment of value for money.

## Compliance Criteria

These criteria are detailed within 5.3.1 of this document and will not be point scored. Each Tender will be assessed on a Yes/No basis as to whether the criterion is satisfactorily met. An assessment of “No” against any criterion may eliminate the Tender from consideration.

## Qualitative Criteria

In determining the most advantageous Tender, the Evaluation Panel will score each Tenderer against the Qualitative Criteria as detailed within 5.3.2 of this document. Each criterion will be weighted to indicate the relative degree of importance that the Principal places on the technical aspects of the goods or services being purchased.

*Note: It is essential that Respondents address each Qualitative Criterion.*

Information that you provide addressing each Qualitative Criterion will be point scored by the Evaluation Panel.

Failure to provide the specified information may result in elimination from the tender evaluation process or a low score.

## Value Considerations

The Weighted Price method is used where price is considered to be crucial to the outcome of the contract. The price is then assessed with quality. Include any items that may affect any pricing outcomes (e.g. Regional Price Preference Policy).

|  |  |
| --- | --- |
| **Criteria** | **Weighting** |
| Most competitive pricing structure.  Council’s assessment of the most advantageous service arrangement based upon Qualitative Criteria | 60%  40% |

## Regional Price Preference

Tenderers for the contract may be afforded a preference in accordance with Regulation 24(A-G) of the *Local Government (Functions and General) Regulations* and the Shire of Waroona Regional Price Preference Policy FP002 - adopted on 25 June 2021.

The Policy stipulates that:

A price preference will apply to tenders invited for procurement over $75,000 by the Shire of Waroona unless Council resolves that this policy not apply to a particular tender invited.

The following levels of preference for the purposes of assessment will be applied under this policy:

1. Shire of Waroona Businesses

* 10% where the contract is for goods and services up to a maximum price assessment reduction of $50,000; and
* 5% where the contract is for construction (building services) up to a maximum price assessment reduction of $50,000.

1. Peel Region Businesses

* 5% where the contract is for goods and services up to a maximum price assessment reduction of $50,000; and
* 2.5% where the contract is for construction (building services) up to a maximum price assessment reduction of $50,000.

The levels of preference will only apply to businesses that are located within the Shire of Waroona or the Peel Region for at least six (6) months prior to the closing date of tender invited.

The level of preference outlined is to be applied as either a local (Shire of Waroona Business or Peel Region Business), not both.

The Peel Region Businesses preference can only be applied if it does not affect the overall evaluation outcomes for a business from the Shire of Waroona, on the condition that the Shire of Waroona Business has submitted an equally competitive bid in terms of evaluated quality i.e.: overall qualitative scores are in the same range/s.

Only the cost of those goods and services clearly identified in the tender submission as being supplied locally or from the Peel Region regionally (regardless of their origin) will be included in the calculation that forms a part of the assessment of a tender. Travel or accommodate costs are excluded.

It should be noted that price is only one factor to be considered when the Shire assesses tender submissions. Value for money principles will be used to achieve the best possible outcome for every dollar spent. This is achieved by assessing all costs and benefits rather than simply selecting the lowest purchase price.

The Peel Region includes the Shire’s of Murray, Boddington, and Serpentine Jarrahdale, and City of Mandurah.

## Price Basis

***Option A: Fixed Prices***

All prices for Works offered under this Request are to be fixed for the term of the Contract. Tendered prices must include Goods and Services Tax (GST).

Unless otherwise indicated prices tendered must include delivery, unloading, packing, marking and all applicable levies, duties, taxes and charges. Any charge not stated in the Tender, as being additional will not be allowed as a charge for any transaction under any resultant Contract.

## Ownership of Tenders

All documents, materials, articles and information submitted by the Tenderer as part of or in support of the Tender will be become upon submission the absolute property of the Principal and will not be returned to the Tenderer at the conclusion of the Tender process PROVIDED that the Tenderer be entitled to retain copyright and other intellectual property rights therein, unless otherwise provided by the Contract.

## Canvassing of Officials

If the Tenderer, whether personally or by an agent, canvasses any of the Principal’s Commissioners, Councillors or Officers (as the case may be) with a view to influencing the acceptance of any Tender made by it or any other Tenderer, then regardless of such canvassing having any influence on the acceptance of such Tender, the Principal may at its absolute discretion omit the Tenderer from consideration.

## Identity of the Tenderer

The identity of the Tenderer and the Contractor is fundamental to the Principal. The Tenderer will be the person, persons, corporation or corporations named as the Tenderer in Part 4 and whose execution appears on the Offer Form in Part 4 of this Request. Upon acceptance of the Tender, the Tenderer will become the Contractor.

## Costs of Tendering

The Principal will not be liable for payment to the Tenderer for any costs, losses or expenses incurred by the Tenderer in preparing their Offer.

## Tender Opening

Tenders will be opened in the Principal’s offices, following the advertised Deadline. All Tenderers and members of the public may attend or be represented at the opening of Tenders.

The names of the persons who submitted the Tender by the due Deadline will be read out at the Tender Opening. No discussions will be entered into between Tenderers and the Principal’s officers present or otherwise, concerning the Tenders submitted.

The Tender Opening will be held on or as soon as practicable after the Deadline atShire of Waroona Administration Office, 52 Hesse Street, Waroona, Western Australia.

## In-house Tenders

The Principal does notintend to submit an In House Tender.

# Statement of Requirements

## Introduction

The Shire (Principal) is seeking a suitably qualified registered building contractor to construct additions and alterations to the existing BIG Shed and to construct a freestanding shelter on Lot 1 Fouracre Street, Waroona

## Background

The Shire has recently upgraded the site around the Big Shed into a landscaped park suitable for public access and playgrounds. The Big Shed structure is a bespoke storage shed to be converted into a space that can be utilised by the public as required for small gatherings.

The request for tender is to construct additions, will include two awning structures with a timber deck on a concrete base as well as a new bespoke internal store structure within the Big Shed, and alterations which will include upgrades to the existing roller doors, new electrical wiring and fixtures and servery counter and shelving.

The Shire have engaged Architects and Engineers to provide drawings and specifications for works required as part of this request and a full list of the associated documents can be found in part “2.4. Scope of Work” of this document.

The Shire has also designed a small shade shelter for the new landscaped park and the construction of the shelter is also included as part of these works.

## Definitions and Interpretations

Below is a summary of some defined terms used in this Part:

|  |  |
| --- | --- |
| **Contractor’s Representative:** | Means any Officer or person duly authorised by the Contractor, in writing, to act on their behalf for the purpose of the Contract; |
| **Principal’s Representative** | Means any Officer of person duly authorised by the Principal, in writing, to act on their behalf for the purpose of the Contract. The Chief Executive Officer of the Shire of Waroona |
| **Works or Services:** | Means the Services, which the Contractor is required to provide to the Principal and the Contractor under the Contract. |
| **Superintendent:** | Shire of Waroona |
| **Superintendent’s Representative:** | Wayne Prangnell |

## Scope of Work

*Perform work described here and shown on drawings including but not necessarily limited to:*

The required works for this request includes the construction of two steel frames awning structures to the north and south of the existing shed. The awning structure will be paint finished with decorative reclaimed timber cladding to the columns. The roof sheeting will be Colorbond finish with no soffit lining.

Existing doors will require new rollers and will need to be removed and reinstated with the new roller installed.

A small portion of the shed (as noted on the drawings) will require repair to the timber girt and new sheeting panels installed.

The shed will require a full clean internally and externally, with new electrical wiring installed together with new electrical distribution board, power points and lighting as noted on the electrical drawings.

A new bespoke internal store will be constructed on the existing shed slab inclusive of new roof sheeting and doors as noted on the drawings. The new electrical distribution board will be located in this room.

A new servery counter and prep bench will be constructed within the shed on the existing shed floor slab. This will require the construction of a new brick wall with lockable doors to prep bench. A new cast in concrete benchtop complete with lockable cupboards will also be constructed.

A new gas cylinder cage with piped gas lines to the new gas BBQ and gas stove will be provided.

A new sink will be provided, and all plumbing will tie into the existing ablution block plumbing adjacent the Big Shed.

The existing concrete floor will be cleaned and re-sealed.

As the surrounding park is well kept and utilised by public, the works area will need to be well kept, secured and all surrounding areas will be made good on completion of the works.

New civil stormwater pipe works will be constructed as per the civil drawings

A new stand-alone shelter is also included as part of the scope of these works. The shelter is located separate from the Big Shed The shelter has a new concrete base, colorbond roof and timber framing using recycled jarrah from the demolition of a scout hall on the site. The Shire has stacked and stored de-nailed timber at the Waroona Shire Depot on Hesse Street which will be provided to the contractor for the construction of the shelter at no charge.

*COOPERATE WITH THESE OTHER TRADES* *to resolve possible problems before starting work.*

Landscape sub-contractor appointed independently by the principal.

*COMPLY WITH APPLICABLE CLAUSES OF THESE BUILDING STANDARDS Current Edition.*

*Comply throughout with the current edition of the Building Code of Australia*

## Drawings and Specifications

Refer to attached Specifications and Drawings for details of the Works;

01 This Document

02 Architectural Drawings

03 Civil & Structural Drawings

04 Electrical Drawings

05 Hydraulic Drawings

06 Architectural Specification

07 Electrical Specification

08 Structural Specification

09 Hydraulic Specification

10 Geotechnical Report

11 Survey

## Implementation Timetable

It is envisaged that this Contract, for the construction of the works will be awarded in April 2025.

The Tenderer’s project programme is to be scheduled from the award date accordingly. If the award date is earlier or delayed, the project programme shall be adjusted and agreed upon accordingly.

The successful Tenderer shall submit for approval by the Principal’s Representative an updated and final programme within seven (7) days of the date of the letter of Award of Contract and, following approval shall become the Contract programme. The Tenderer’s performance shall be monitored and measured against the Contract programme. The programme may only be modified by the Principal’s Representative in writing following receipt and consideration of a request in writing by the Tenderer setting out the reasons for modification. If the programme is modified in accordance with the aforementioned process, the modified programme shall become the Contract programme and replace all preceding programmes.

## Contract Documents

The following items shall form the Contract Documents and shall be read in conjunction with each other:

1. Conditions of Tendering,
2. The Tenderer’s Offer,
3. Correspondence between the parties agreed to be included in the contract prior to the signing of the Formal Instrument of Agreement,
4. The Letter of Acceptance,
5. Formal Instrument of Agreement,
6. Contract Sum Schedules,
7. Australian Standard General Conditions of Contract AS 2124-1992 (as amended),
8. Annexure to the Australian Standard General Conditions of Contract AS 2124-1992 - Part A,
9. Annexure to the Australian Standard General Conditions of Contract AS 2124-1992 – Part B amended clauses and additional clauses,
10. Specifications;
11. Drawings, and the
12. Superintendent's instructions and other documents which may be issued by the Superintendent to the Contractor in accordance with the Conditions of Contract.

and the whole shall constitute one document.

## Reporting and Records

Reporting and records keeping requirements are dealt as per (add details).

## Goods and Services Tax (GST)

For the purposes of this clause:

1. “GST” means goods and services tax applicable to any taxable supplies as determined under the GST Act.
2. “GST Act” means *A New Tax System (Goods and Services Tax) Act 1999* and (where the context permits) includes the Regulations and the Commissioner of Taxation’s Goods and Services Tax Rulings and Determinations made thereunder and any other written law dealing with GST applying for the time being in the State of Western Australia.
3. “Supply” and “taxable supply” have the same meanings as in the GST Act.

Where the Requirement’s, the subject of this Request, or any part thereof is a taxable supply under the GST Act, the price, fee or rates tendered by the Tenderer shall be inclusive of all applicable GST at the rate in force for the time being.

In evaluating the Tenders, the Principal shall be entitled (though not obliged) to take into account the effect of the GST upon each Tender.

# Conditions of Contract

## Terms and Conditions of Contract

The Terms and Conditions of Contract shall be Australian Standard AS 2124

## Contract Schedules

With reference to AS2124 1992 Contract the following Schedules shall apply

Copy of Annexure to General Conditions of Contract:

|  |  |
| --- | --- |
| The law applicable is that of the State or Territory of: (Clause 1) | Western Australia |
| Payments under the Contract shall be made at: (Clause 1) | Perth W.A. - by way of “not negotiable” cheque or Electronic Funds Transfer to the account nominated by the Contractor/Principal |
| The Principal is: (Clause 2) | SHIRE OF WAROONA |
| The address of the Principal is: | 52 Hesse Street, Waroona, WA 6215 |
| The Superintendent shall be: (Clause 2) | SHIRE OF WAROONA |
| The address of the Superintendent is: | 52 Hesse Street, Waroona, WA 6215 |
| Limits of accuracy applying to quantities for which the Principal accepted a rate or rates: (Clause 3.3(b)) | Not Applicable |
| Bill of Quantities - The alternative applying: (Clause 4.1) | Not Applicable |
| The time for lodgement of the priced copy of the Bill of Quantities is: (subclause 4.2) | Not Applicable |
| # Contractor shall provide security in the amount of: (Clause 5.2) | Five (5) % of the Contract Sum |
| # Principal shall provide security in the amount of: (Clause 5.2) | Not Applicable |
| # The period of notice required of a party’s intention to have recourse to retention moneys and/or to convert security: (Clause 5.5) | 14 Calendar days |
| The percentage to which the entitlement to security and retention moneys is reduced: (Clause 5.7) | 50% |
| Interest on retention moneys and security - the alternative applying: (Clause 5.9) | Alternative 2 |
| The number of copies to be supplied by the Principal: (Clause 8.3) | Three (3) |
| The number of copies to be supplied by the Contractor: (Clause 8.4) | Three (3) |
| The time within which the Superintendent must give a direction as to the suitability and return the Contractor’s copies: (Clause 8.4) | 14 days |
| Work which cannot be subcontracted without approval: (Clause 9.2) | Works relating to any Provisional Sums |
| The percentage of profit and attendance: (Clause 11(b)) | Ten (10)% |
| The amount or percentage for profit and attendance: (Clause 11(c)) | Ten (10)% |
| Insurance of the Works - the alternative applying: (Clause 18) | Alternative 1 |
| The assessment for insurance purposes of the costs of demolition and removal of debris: (Clause 18(ii)) | 10% of Value of Work |
| The assessment for insurance purposes of consultants’ fees: (Clause 18(iii)) | 10% of Value of Work |
| The value of materials to be supplied by the Principal: (Clause 18(iv)) | $ 1500.00 |
| The additional amount or percentage: (Clause 18(v)) | 5% |
| Public liability insurance - the alternative applying: (Clause (19) | Alternative 1 |
| The amount of Public liability insurance shall be not less than: (Clause 19) | $20 Million |
| The time for giving possession of the Site: (Clause 27.1) | Within 21 days of Date of Acceptance of Tender |
| # The datefor Practical Completion: (Clause 35.2) | **20** weeks after date of Possession.  Date of Possession anticipated early April 2025. |
| # Liquidated damages per day: (Clause 35.6) | $100 per calendar day |
| # Limitof Liquidated damages: (Clause 35.7) | Unlimited |
| # Bonus per day for early Practical Completion: (Clause 35.8) | Not Applicable |
| # Limitof bonus: (Clause 35.8) | Not Applicable |
| # Extra costs for Delay or Disruption: (Clause 36) | Nil |
| # TheDefects liability period: (Clause 37) | Twelve (12) Months |
| The charge for overheads, profit etc. for daywork: (Clause 41(f)) | Ten (10) % Of the value of the cost of the works |
| Times for Payment claims: (Clause 42.1) | Same Date each Month – to be agreed |
| Unfixed plant and materials for which payment claims may be made notwithstanding that they are not incorporated in the Works: (Clause 42.1 (ii)) | Not Applicable |
| Retention moneys on: (Clause 42.3) | Work incorporated in the works and any work or items for which a different amount of retention is not provided 10% of the value until 5% of the Contract Sum is held. |
| Unfixed plant or materials - the alternative applying: (Clause 42.4) | Alternative 1 |
| The rate of interest on overdue payments: (Clause 42.9) | Supreme Court rates as at the Date of Acceptance of the Tender |
| The delay in giving possession of the site which shall be a substantial breach: (Clause 44.7) | 28 days |
| The alternative required in proceeding with dispute resolution: (Clause 47.2) | Alternative 1 |
| The person to nominate an arbitrator: (Clause 47.3) | No person nominated |
| Location of arbitration: (Clause 47.3) | Western Australia |

## SEPARABLE PORTIONS – Not Applicable

## Insurances

Without limiting its obligations and responsibilities, the successful Tenderer shall take out insurances for the entire contract period under the following headings:

1. Public and Products Liability ($20m)
2. Workers Compensation: The Contractor shall effect and keep in effect during the currency of the Contract such Insurance as may be necessary to adequately protect the Contractor and the Principal in respect of liability for payment of compensation to any Employee of the Contractor or of a subconsultant of the Contractor under the Workers’ Compensation and Injury Act 1981 or at Common Law.
3. The Works

## Period of Contract Termination

The Contract will be in force from the date of the execution of the Contract documentation.

The Contract is to be completed in accordance with the above contract.

However, in the event of the Contractor failing in any manner to carry out the Contract to the Principal’s satisfaction, the Principal may forthwith determine the Contract by written notice to the Contractor.

Should significant addition time be required on site to conform to unforeseen delays beyond the Principal’s control such as and not limited to adverse weather conditions, transport difficulties, airport/plane delays/re-scheduling the Principal will not be held accountable for any additional cost incurred by the successful Contractor unless prior approval is given by the Chief Executive Officer or their delegated officer.

# Special Conditions of Contract

## Advertisements and Promotions on Site

The Contractor may erect on the Site or permit to be erected on Site only those signs:

1. required by law;
2. specified in the Contract documents; and
3. required to identify the Contractor’s premises

The Contractor shall not erect on Site, or permit to be erected on site, any other sign, advertisement, promotion or other display without the written approval of the Superintendent.

## Site Access

The Big Shed will not be occupied during the currency of the contract, however the park on which The Shed is located will remain open to the public. The contractor will be required to secure the work site using temporary site fencing to ensure public safety and separation from the works sites at all times. The Shire of Waroona will provide access to temporary fencing for use on the site, refer cl 4.8 Temporary Safety Fence.

The contractor shall ensure staff and subcontractors are polite and respectful to members of the public.

Pets are not permitted on site.

## Publicity

The Contractor shall not issue any information, publication, document or article for publication in any media which includes details of the work under the Contract without the written approval of the Principal.

## Documents Generally, Drawings and Specifications

### Copies of Documents

Where the Contractor requires copies of the documents in addition to its entitlements to one (1) such additional copies of the documents will be available to the Contractor at the charge current at the time of request.

### Drawings

The Contractor is to provide the Principal with a copy of all relevant approved drawings.

## Environmental Protection

### Noise Control

The Contractor shall, at all times, take adequate measures to control noise on the Site.

The contractor shall comply with all statutory requirements relating to control of noise levels on the Site and take all necessary precautions to minimise nuisance from noise and vibration and ensure that all sub-contractors observe similar care.

The Contractor shall arrange the operations and shall provide silencing equipment to the plant, at its own expense, to whatever extend it necessary to satisfy the requirements of the relevant authority in relation to the sound level arising from the Contractor’s operations near the boundaries of existing occupied properties.

### Site Control

The Contractor shall, at all times:

1. Comply with the regulations and restrictions imposed by the Superintendent relating to the storage of materials, the routing of construction traffic, the interruption of existing services and facilities and any other regulations in force on the Site;
2. Comply with all statutes, regulations and bylaws relating to the protection of the environment;
3. Obtain written approval from the Superintendent for the formation of any temporary roads, the erection of temporary structures or any Site clearing not specifically documented;
4. Ensure that no trees or shrubs shall be removed or destroyed without the written approval of the Superintendent;
5. Ensure that no fire shall be lit without the written approval of the Superintendent; and
6. Store flammable or explosive products in accordance with the relevant statutes and to the approval of the Superintendent.

### Soil Erosion

The contractor shall take all proper precautions to prevent soil erosion from any land used or occupied by the Contractor in the execution of the work under the Contract.

### Dust, Dirt, Water and Fumes

The contractor shall prevent any nuisance occurring through the discharge of dust, dirt, water, fumes and the like onto persons or property.

### Vehicles

All debris, spoil, rubbish or materials shall be suitably contained and covered in vehicles during transportation to or from the Site to prevent spillage or contamination of adjoining and other areas or property.

The Contractor shall maintain vehicles, wheels and tracks in a suitable clean condition to prevent transfer of mud onto adjacent streets or other areas.

### Refuse Disposal

All Site refuse (including foodstuffs) shall be handled and disposed of in accordance with the requirements of relevant statutes and to the approval of the Superintendent.

### Smoking on Construction Sites

The Contractor shall at all times ensure that all workmen and visitors on the construction Site comply with the following Smoking Policy;

In respect of construction Sites, smoking is prohibited:

1. in Site Offices, lunchrooms or enclosed toilet facilities; and
2. inside existing premises that are designated as “no smoking” areas.

### Contractor’s Representative

The Contractor’s Representative shall have sufficient command of the English language and of Australian construction and technical terminology, to be able to read, converse and receive instructions in English.

### Existing Improvements

Where, within the Site there are a range of existing improvements, roads, drainage and other services, the Contractor shall protect and maintain these throughout the Contract.

### Temporary Safety Fence

The Contractor shall install temporary site fencing as required by the Work Health and Safety Act 2020 (the “Act”) and the Work Health and Safety (General) Regulations 2022 and with any amendments that may be made to the Act and the Regulations.

The Shire of Waroona will supply temporary fencing panels to the contractor at the Shire depot on Hesse St Waroona no cost for the purpose of installing a site safety fence. The contractor will be responsible for the collection, transport, installation, maintenance, removal and return of the temporary fencing.

## Materials, Labour and Constructional Plan

## Workmen’s Amenities

Use of the existing public amenities on the site for use by workers shall be permitted.

### Materials and Work

## Regulations

The Contractor shall comply with the Work Health and Safety Act 2020 (the “Act”) and the Work Health and Safety (General) Regulations 2022 (the “Regulations”) and with any amendments that may be made to the Act and Regulations from time to time.

The Contractor shall be solely responsible for ensuring that wherever practicable, its employees and those of the Sub-contractors and employees of Separate Contractors, the Principal, Superintendents, and visitors to the Site, are not exposed to hazards.

Attention is drawn to the requirement to supply manufacturers/suppliers “Material Safety Data Sheets”. These sheets should be consistent with the “Work Safe” information and format.

A copy of all “Material Safety Data Sheets” shall be supplied to the Superintendent with another copy kept on Site by the Contractor.

## Chemical Information

The use of chemicals specified or required during the currency of this Contract shall comply with the requirements of the Act and associated Regulations concerning information on chemical substances.

The Contractor shall ensure manufacturers, importers and suppliers of chemical substances for use on the works, are responsible for providing information on those substances to be used, refer to Section 23(3) of the Act.

Copies of all information supplied shall be kept on the Site.

The Contractor is responsible for passing on information supplied by manufacturers; importers and suppliers of chemical substances to workers on Site refer to Section 19(1)(B) of the Act.

## Trade Names

Where a trade name, brand or catalogue number is referred to in the Contract, the Contractor may substitute equivalent material or equipment provided that in the opinion of the Superintendent the characteristics of type, quality, finish, appearance, method of construction and performance are not less than that specified, and are approved by the Superintendent.

Such approval shall not be anticipated because of similar approval having been given in a previous contract.

## Safety Management Plan

The Contractor shall, throughout the Works, implement and maintain a “Safety Management Plan”.

The Contractor shall prepare the Safety Management Plan in conjunction with a person suitably experience and qualified in safety matters.

Prior to the commencement of the Works, the Contractor shall supply to the Superintendent in writing, its Safety Management Plan.

The Safety Management Plan shall also address measures to manage the safe public access and use of parts of the site (public park) that are not subject to building works.

## Induction Training

Employees of the Contractor and its Subcontractors and Employees of Separate Contractors shall not commence work on the Site until they have been inducted.

Upon commencement of work on the Site, the Contractor shall further induct each employee with regard to all significant hazards associated with their particular activity and area of employment on the Site and where relevant shall include the use of powered plant, tools and equipment.

## Pre-Job Planning

Where legislation or codes of practice identify particularly hazardous activities including but not limited to work in confined spaces, asbestos removal, demolition work, excavation work, working near power lines and live conductors and working at heights, the Contractor shall supply to the Superintendent a Safe Work Procedure prior to the commencing such activity or type of work on the Site.

The Contractor shall induct its employees and its Subcontractors and Separate Contractors with regard to Safe Work Procedures and shall prepare “Training Session Attendance” sheets signed by each attendee verifying that such induction has occurred.

## Materials to be Supplied by the Principal

The materials stated in the specification (recycled Jarrah timber for freestanding shelter and site safety fence) to be supplied by the Principal will be supplied free of charge to the Contractor for use only in the execution of the work under the Contract. The Contractor shall take delivery of the materials under the Conditions set out in the Contract.

## Working Hours

The Work to be performed under the contract shall be determined by the Contractor in conjunction with the Principal.

The Contractor shall be liable for any additional costs the Principal may incur as a result of work outside the normal hours programming of the works.

## Schedule of Warranties

The Contractor shall obtain and ensure that the Principal will have the benefit of all warranties specified in the Contract including the following items of work, materials or equipment.

## Goods and Services Tax (GST)

For the purposes of this clause:

1. “GST” means goods and services tax applicable to any taxable supplies as determined under the GST Act.
2. “GST Act” means A New Tax System (Goods and Services Tax) Act 1999 and (where the context permits) includes the Regulations and the Commissioner of Taxation’s Goods and Services Tax Rulings and Determinations made thereunder and any other written law dealing with GST applying for the time being in the State of Western Australia.
3. “Supply” and “taxable supply” have the same meanings as in the GST Act.

Where the Requirement’s, the subject of this Request, or any part thereof is a taxable supply under the GST Act, the price, fee or rates tendered by the Tenderer shall be inclusive of all applicable GST at the rate in force for the time being.

In evaluating the Tenders, the Principal shall be entitled (though not obliged) to take into account the effect of the GST upon each Tender.

## BCITF Levy

Where a building and or Civil Engineering Contract exceeds the value of $20,000, the Contractor will pay the training levy fee in accordance with the Building and Construction Industry Training Levy Collection Act 1990.

The Contractor shall lodge a certificate of proof with the Principal prior to commencement of construction.

# Tenderer’s Offer

## Form of Tender

|  |  |
| --- | --- |
| **TO:** | The Chief Executive Officer  Shire of Waroona  52 Hesse Street  WAROONA WA 6215 |

I/We (Registered Entity Name): \_\_\_\_\_\_\_\_\_\_\_

(BLOCK LETTERS)

of: \_\_\_\_\_\_\_\_\_\_\_

(REGISTERED STREET ADDRESS)

ABN \_\_\_\_\_\_ (if any)

Telephone No: \_\_ \_ Facsimile No: \_\_\_\_\_ \_\_\_\_\_

E-mail: \_\_\_\_\_\_\_\_\_\_\_

|  |  |
| --- | --- |
| In response to Request for Tender (RFT) 2425-04, Big Shed additions and alterations to construct additions and alterations to the Big Shed and a new freestanding shelter, Fouracre St Waroona I/We hereby tender to perform the construction of the building works and all associated works, in accordance with the Conditions of Contract, The Specification, and the Drawings, for the (GST inclusive) lump sum price of: | |
|  | |
|  | $ |
| We confirm receipt of and allowance for addenda numbers: \_\_\_\_\_ |  |
|  |  |

I/We agree that I am/We are bound by and will comply with this Request and its associated schedules, attachments, all in accordance with the Conditions of Tendering contained in this Request signed and completed.

The tendered price is valid up to ninety (90) calendar days from the date of the tender closing or forty-five (45) days from the Council’s resolution for determining the Tender, whichever is the later unless extended on mutual agreement between the Principal and the Tenderer in writing.

I/We agree that there will be no cost payable by the Principal towards the preparation or submission of this Tender irrespective of its outcome.

The tendered consideration is as provided under the schedule of rates of prices in the prescribed format and submitted with this Tender.

Dated this \_\_\_\_\_\_ day of \_\_\_\_20 \_

Signature of authorised signatory of Tenderer: \_\_\_\_\_\_\_

Name of authorised signatory (BLOCK LETTERS): \_\_\_\_\_\_\_\_\_\_\_\_\_

Position: \_\_\_\_\_\_\_\_\_\_\_\_\_

Telephone Number: \_\_\_\_\_\_\_\_\_\_\_\_\_

Authorised signatory Postal address: \_\_\_\_\_\_\_

Email Address: \_\_\_\_\_\_\_

### Price Schedule

The prices entered shall fully cover all the obligations of the Contractor under the Contract. Please add or remove tasks as applicable.

Trade Breakdown of Price Schedule

Tenderers shall complete the following Tender Sum Breakdown, in the exact format shown, and submit it together with the Tender Offer Form. Non-compliance with this requirement may render the tender submission invalid.

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Trade** | **Details if required** | **Value $ (Excl. GST)** |
| 1 | Preliminaries |  |  |
| 1.1 | Insurances |  |  |
| 1.2 | Site Establishment | Including accommodation, mobilisation and demobilisation, fencing |  |
|  |  |  |  |
| 2 | **Big Shed** |  |  |
| 2.1 | Earthworks |  |  |
| 2.2 | Concrete works | External paving |  |
| 2.3 | Concrete works | Shed and Toilets |  |
| 2.4 | Brickwork |  |  |
| 2.5 | Structural Steel | Include steel treatment system |  |
| 2.6 | Wall and Roof framing | Steel |  |
| 2.7 | Roofing | Including roof plumbing and RWPs |  |
| 2.8 | External cladding |  |  |
| 2.9 | Wall linings | Including Stud framing |  |
| 2.10 | Timber Decking |  |  |
| 2.11 | Door frames |  |  |
| 2.12 | Sliding door rollers |  |  |
| 2.13 | Joinery | Doors including reclaimed timber to columns |  |
| 2.14 | Cabinetry | Include associated reclaimed timber |  |
| 2.15 | Ceramic Tiling | Include screeds & w/proofing |  |
| 2.16 | Painting | External and Internal |  |
| 2.17 | Mechanical Works | Extract vents |  |
| 2.18 | Electrical Works |  |  |
| 2.19 | Hydraulic Works |  |  |
| 2.20 | Gas works | Including Gas bottle cage |  |
| 2.21 | Stormwater Works | In-ground works |  |
|  |  |  |  |
| **3** | **Freestanding Shelter** |  |  |
| 3.1 | Earthworks |  |  |
| 3.2 | Concrete Slab |  |  |
| 3.3 | Framing & Roof |  |  |
|  |  |  |  |
| 4 | Provisional Sum | Additional works as directed by the Principal | $40,000.00 |
|  |  |  |  |
|  |  | SUB - TOTAL |  |
|  |  | GST |  |
| TENDER SUM | TENDER SUM | TOTAL – INCLUDING GST |  |

## General and Corporate Information

The Tenderer shall complete and submit all sections of Part 5. Where an item is Not Applicable is should be marked “N/A” and an explanation provided, where appropriate, of why it is not applicable.

### Organisational Profile and Referees

|  |  |
| --- | --- |
| Attach the profile of the person, entity or corporation that is making the Tender and label it **“Attachment 1 – Organisation Profile”**.  The profile MUST BE OF ‘the Tenderer’. The Tenderer must be a legal entity capable of entering into a contractual arrangement in the Tenderer’s name. | **Attachment 1**  Tick if attached |
| If the Tenderer is comprised of companies, attach their current ASIC company extracts search including latest annual return and label it **“Attachment 2 – ASIC documentation”**. | **Attachment 2**  Tick if attached |
| Attach details of your referees and label it **“Attachment 3 – Referees”**. You should give examples of work provided for referees listed. | **Attachment 3**  Tick if attached |

### Agents

|  |  |
| --- | --- |
| Are you acting as an agent for another party? | Yes / No |
| If Yes, attach details (including name, address, telephone, background information) of your principal and label it **“Attachment 4 – Acting as Agent”**. | **Attachment 4**  Tick if attached |

### Trusts

|  |  |
| --- | --- |
| Are you acting as a trustee of a trust? | Yes / No |
| If Yes, in an attachment labelled **“Attachment 5 – Acting as Trustee”**:  (a) give the name of the trust; and (b) provide the names and addresses of beneficiaries. | **Attachment 5**  Tick if attached |

### Sub-Contractors

|  |  |
| --- | --- |
| Do you intend to subcontract any of the Requirements? | Yes / No |
| If Yes, attach details of the Sub-contractor(s) including the name, address, location of premise and the number of people employed with details of works provided and label it **“Attachment 6 – Sub-contractors”**. | **Attachment 6**  Tick if attached |

### Conflicts of Interest

|  |  |
| --- | --- |
| Will any actual or potential conflict of interest in the performance of your obligations under the Contract exist if you are awarded the Contract and are any such conflicts of interest likely to arise during the Contract? | Yes / No |
| If Yes, please supply in an attachment details of any actual or potential conflict of interest and the way in which any conflict will be dealt with and label it **“Attachment 7 – Conflict(s) of Interest”**. | **Attachment 7**  Tick if attached |

### Work Health and Safety

|  |  |
| --- | --- |
| The Contractor will:   * Provide all Occupation Work Health and Safety documentation * Complete pre-qualification WH&S induction if successful * Complete site induction with principal representative if successful   A full statement of the goods and/or services required appears in the Specification. | Yes / No |
| If Yes, please supply in an attachment details of any and label it **“Attachment 8 – Work Health and Safety”**. | **Attachment 8**  Tick if attached |

### Financial Position

|  |  |
| --- | --- |
| Are you presently able to pay all your debts in full as and when they fall due? | Yes / No |
| Are you currently engaged in litigation as a result of which you may be liable for $50,000 or more? | Yes / No |
| If you are awarded the Contract, will you be able to fulfil the Requirements from your own resources or from resources readily available to you and remain able to pay all of your debts in full as and when they fall due? | Yes / No |
| Attach a financial profile for you and your Sub-contractors (if any), that demonstrates your (and their) financial capacity, together with a list of financial referees.  This may include Annual Financial Statements (Profit & Loss, Balance Sheet), Bank Guarantee and/or Accountant’s Statement(s).  Attach and label it **“Attachment 9 – Financial Profile and Referees”**. | **Attachment 9**  Tick if attached |

### Quality Assurance System

|  |  |
| --- | --- |
| Does your organisation have any quality assurance or quality assurance systems? Or substantially working towards? | Yes / No |
| If you propose to subcontract, does your Sub-contractor have a “third party” quality management system in place? | Yes / No |
| Supply evidence or details of your quality assurance position and where relevant your supplier’s or Sub-contractor’s position, in an attachment labelled **“Attachment 10 – Quality Assurance”**. | **Attachment 10**  Tick if attached |

### Insurance Coverage

|  |  |
| --- | --- |
| The insurance requirements for this Request are stipulated in the Special Conditions. Tenderers are to supply evidence of their insurance coverage in a format as outlined below in **“Attachment 11 - Insurance Coverage”**. A copy of the Certificate of Currency is to be provided to the Principal before acceptance of Offer. | **Attachment 11**  Tick if attached |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Type** | **Insurer – Broker** | **Policy Number** | **Value ($)** | **Expiry Date** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

The insurance requirements for this Request are stipulated in Part 3 of this Request. Tenderers are to supply evidence of their insurance coverage including, insurer, expiry date, value and type of insurance. If the Tenderer holds “umbrella Insurance” please ensure a breakdown of the required insurances are provided. A copy of the Certificate of Currency is to be provided to the Principal within 2 days upon request.

Failure to provide details of insurance coverage in accordance with the specified insurance levels stated in this Request document may eliminate the Tender from consideration at the Principals’ discretion.

The required insurances must remain current for the duration of the Contract.

## Selection Criteria

### Compliance Criteria

Please select with a “Yes” or “No” whether you have complied with the following compliance criteria:

|  |  |
| --- | --- |
| **Description of Compliance Criteria** |  |
| Respondents are to provide acknowledgment that your organisation has submitted in accordance with the Conditions of this RFQ including completion of the Offer Form and provision of your pricing submitted in the format required by the Principal. | Yes / No |
| Compliance with the Specification contained in the Request. | Yes / No |
| Compliance with attendance at any mandatory briefing or site inspection. | Yes / No |
| Compliance with the Quality Assurance requirement for this Request. | Yes / No |
| Compliance with the Delivery Date. | Yes / No |

### Qualitative Criteria

Before responding to the following Qualitative Criteria, Tenderers must note the following:

1. All information relevant to your answers to each criterion are to be contained within your Tender;
2. Tenderers are to assume that the Evaluation Panel has no previous knowledge of your organisation, its activities or experience;
3. Tenderers are to provide full details for any claims, statements or examples used to address the Qualitative Criteria; and
4. Tenderers are to address each issue outlined within a Qualitative Criterion.

|  |  |
| --- | --- |
| 1. **Relevant Experience**   Describe your experience in supplying similar Requirements.Tenderers must, as a minimum, address the following information in an attachment and label it **“Attachment 13 - Relevant Experience”**:   1. Provide details of similar work; 2. Provide scope of the Tenderer’s involvement including details of outcomes. 3. Provide details of issues that arose during the project and how these were managed; 4. Demonstrate competency and proven track record of achieving outcomes. | **Weighting**  **10%** |
| **Attachment**  Tick if attached |
|  |  |
| **B) Key Personnel Skills and Experience**  Tenderers should provide as a minimum information of proposed personnel to be allocated to this project, such as:   1. Their role in the performance of the Contract; 2. Curriculum vitae; 3. Membership to any professional or business associations; 4. Qualifications, with particular emphasis on experience of personnel in projects of a similar requirement; and 5. Any additional information.   Supply details in an attachment and label it **“Attachment 14 - Key Personnel”**. | **Weighting**  **10%** |
| **Attachment**  Tick if attached |
|  |  |
| 1. **Tenderer’s Resources**   Tenderers should demonstrate their ability to supply and sustain the necessary:   1. Plant, equipment and materials; 2. Any contingency measures or back up of resources including personnel (where applicable); 3. OSH Survey; 4. Safety Record; and 5. Resources Schedule.   Tenderers should provide a current commitment schedule and plant/equipment schedule in an attachment and label it **“Attachment 15 - Tenderer’s Resources”**. | **Weighting**  **10%** |
| **Attachment**  Tick if attached |
|  |  |
| 1. **Demonstrated Understanding**   Tenderers should detail the process they intend to use to achieve the Requirements of the Specification. Areas that you may wish to cover include:   1. A project schedule/timeline (where applicable); 2. The process for the delivery of the works; and 3. A demonstrated understanding of the scope of work.   Supply details and provide an outline of your proposed methodology in an attachment labelled **“Attachment 16 - Demonstrated Understanding”**. | **Weighting**  **10%** |
| **Attachment**  Tick if attached |

|  |  |
| --- | --- |
| 1. **Cost**   Tenderers are to complete the Price Schedule Refer: 5.4 Price Information | **Weighting**  **60%** |

## Price Information

Tenderers must complete the “Price Schedule” in Clause 5.1.1. Before completing the Price Schedule, Tenderers should ensure they have read this entire Request.

Tendered total prices must include Goods and Services Tax (GST).

Unless otherwise indicated prices tendered must include delivery, unloading, packing, marking and all applicable levies, duties, taxes and charges.

## Discounts

|  |  |
| --- | --- |
| Are you prepared to allow discount for prompt settlement of accounts? | **Yes / No** ⬜⬜ |
| If you are offering discounts for different periods, or other discounts such as volume discounts, detail them in an attachment labelled “**Discounts**”. | **“Discounts”** |

## Price Basis

|  |  |
| --- | --- |
| Are you prepared to offer a lump sum price? | **Yes / No**  ⬜⬜ |

## Regional Preference

|  |  |
| --- | --- |
| Do you wish to claim regional price preference for Shire of Waroona  Do you wish to claim regional price preference for Peel Region  What proportion of your lump sum price will be completed by contractors, subcontractors and material suppliers in the Waroona Shire  What proportion of your lump sum price will be completed by contractors, subcontractors and material suppliers in the Peel Region | **Yes / No**  ⬜⬜  **Yes / No**  ⬜⬜  **\_\_\_%**  **\_\_\_%** |

# Contractor’s Work Health and Safety Management System Questionnaire

This questionnaire forms part of the Principal’s Tender evaluation process and is to be completed by tenderers and submitted with their Tenders and labelled as “**Contractor’s Safety & Health Questionnaire**”. The objective of the questionnaire is to provide an overview of the status of Contractor’s safety management system. Contractors may be required to verify their responses noted in their questionnaire by providing evidence of their ability and capacity in relevant matters.

|  |  |  |
| --- | --- | --- |
| **OSH Policy and Management** | **Yes** | **No** |
| Is there a written company Health and Safety Policy?  If Yes, provide a copy of the policy. | ⬜ | ⬜ |
| Does the company have an OSH Management System?  If Yes, provide details:  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Is the OSH Management System audited or reviewed on a regular basis?  If Yes, provide details of last audit and outcomes.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Are Line Managers held accountable for Health and Safety performances?  If Yes, provide details  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |

|  |  |  |
| --- | --- | --- |
| **Safe Workplace Practices and Procedures** | **Yes** | **No** |
| Has the company prepared Safe Operating Procedures or specific safety instructions relevant to its operations?  If Yes, provide a summary listing of procedures or instructions.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Are safe operating procedures or specific safety instructions issued to employees?  If Yes, explain how this is done.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Does the company have any Permit to Work systems?  If Yes, provide a copy of a standard Incident Report form. | ⬜ | ⬜ |
| Are there procedures for storing and handling hazardous substances?  If Yes, provide details.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| **Occupational Safety and Health** |  |  |
| Describe how Safety and Health Training is conducted in your company?  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | | |
| Provide details of any company safety induction programmes for company employees and or subcontractors.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | | |

|  |  |  |
| --- | --- | --- |
| **Safety and Health Workplace Inspection** | **Yes** | **No** |
| Are regular Health and Safety Inspections at work Sites undertaken?  If Yes, provide details.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Are standard workplace inspection checklists used to conduct Health and Safety Inspections?  If Yes, provide details or examples.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Is there a procedure by which employees can report hazards at workplaces?  If Yes, provide details  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |

|  |  |  |
| --- | --- | --- |
| **Safety and Health History** | **Yes** | **No** |
| Is there a system for recording and analysing Safety Performance Statistics?  If Yes, provide details.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |
| Has the company ever been convicted of a Work Health and Safety offence?  If Yes, provide details.  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_  \_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_ | ⬜ | ⬜ |

# Tenderer’s Resource Schedule

## 7.1. Tenderer’s Current Commitment Schedule

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Project** | **Description** | **Value as Let** | **Date Started** | **Referees Name**  **Telephone Number** |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |
|  |  |  |  |  |

# Appendix A – Architectural works specification

# 9. Appendix B – Electrical works specification

# 10. Appendix C – Hydraulics works specification

# 11. Appendix D – Structural works specification

# 12. Appendix E – Drawings